## Summary
MojiTax Connect - Production Readiness Summary
Audit Date: | December 18, 2025
Total Features Audited: | 78
Test Results:
✅ PASS (Working) | 12 | 15.4%
❌ FAIL (Not Implemented) | 37 | 47.4%
⚠️ PARTIAL (Partially Working) | 22 | 28.2%
⚠️ UNKNOWN (Not Tested) | 7 | 9.0%
User Impact Priority:
🔴 CRITICAL | 8
🟠 HIGH | 25
🟡 MEDIUM | 37
🟢 LOW | 8
Production Readiness: | 15.4%
Estimated Timeline to Production: | 7-11 weeks
Top 5 Critical Issues:
1. mojitax.co.uk OAuth Integration - Cannot launch without real authentication
2. 'Chat with Team MojiTax' Functionality - Core support channel completely broken
3. Email Notifications for Support - Admin won't know about user requests
4. Terms of Service & Privacy Policy - Legal requirement
5. Admin Login Security - Currently anyone can access admin area

## Production Audit
# | Feature Category | Feature Name | User Type | Expected Functionality | Current State | Test Result | User Impact | Actions Required for Production
1 | Authentication & Onboarding | Name Prompt Dialog | All Users | Users enter their name on first visit to identify themselves in chat | ✅ WORKING - Dialog appears, accepts input, stores in localStorage | ✅ PASS | HIGH | • Replace with mojitax.co.uk OAuth integration • Add profile picture upload • Add email capture • Add terms of service acceptance
2 | Authentication & Onboarding | Login Button/Flow | mojitax.co.uk Users | Authenticated users should see 'Login with MojiTax' button and OAuth flow | ❌ NOT IMPLEMENTED - No visible login button or OAuth flow | ❌ FAIL | CRITICAL | • Add 'Login with MojiTax' button in header • Integrate mojitax.co.uk OAuth • Show authentication state (logged in/out) • Add logout button
3 | Authentication & Onboarding | User Profile Display | All Users | Show user name, avatar, role badge in header | ⚠️ PARTIAL - Shows 'MO' initials only, no dropdown or profile info | ⚠️ PARTIAL | MEDIUM | • Add user dropdown menu • Show full name and email • Add profile edit option • Add logout option
4 | Authentication & Onboarding | Guest vs Authenticated State | All Users | Clear visual distinction between guest and authenticated users | ❌ NOT IMPLEMENTED - All users appear the same | ❌ FAIL | MEDIUM | • Add 'Guest' badge for unauthenticated users • Show limited features for guests • Prompt guests to sign up
5 | Chat with Team MojiTax | 'Chat with Team MojiTax' Button | mojitax.co.uk Users | Opens private support channel where users can ask questions; @moji responds first, escalates to human if needed | ❌ NOT FUNCTIONAL - Button exists but does nothing when clicked | ❌ FAIL | CRITICAL | • Create dedicated support channel in database • Add click handler to open support channel • Show welcome message explaining @moji will help first • Add 'Request Human Agent' button • Create support ticket when escalating
6 | Chat with Team MojiTax | Support Channel Welcome Message | mojitax.co.uk Users | Clear explanation that @moji will try to answer questions, and human agents available during business hours | ❌ NOT IMPLEMENTED - No welcome message | ❌ FAIL | HIGH | • Add auto-message when opening support channel • Explain @moji capabilities • Show business hours (UK time) • Add response time expectations
7 | Chat with Team MojiTax | @moji Auto-Response in Support | mojitax.co.uk Users | @moji automatically responds to questions without needing @mention | ⚠️ PARTIAL - @moji works but requires @mention | ⚠️ PARTIAL | MEDIUM | • Auto-trigger @moji for all messages in support channel • Remove need for @mention in support context • Add typing indicator while @moji thinks
8 | Chat with Team MojiTax | Escalation to Human Agent | mojitax.co.uk Users | 'Talk to Human' button creates support ticket and notifies admin@mojitax.com | ⚠️ BACKEND ONLY - Support ticket system exists but no user-facing button | ⚠️ PARTIAL | HIGH | • Add 'Request Human Agent' button in support channel • Create modal to collect issue details • Send email to admin@mojitax.com • Show confirmation message with ticket number
9 | Chat with Team MojiTax | Support Ticket Status Tracking | mojitax.co.uk Users | Users can see their open/closed tickets and status updates | ❌ NOT IMPLEMENTED - No user-facing ticket view | ❌ FAIL | MEDIUM | • Add 'My Tickets' section in user profile • Show ticket status (open, in-progress, closed) • Show last admin response • Send email when admin replies
10 | Topic Channels | General Channel | All Users | Public discussion for general tax topics, shows message history | ✅ WORKING - Can send/receive messages, see history | ✅ PASS | HIGH | • Add channel description/rules • Add pinned welcome message • Moderate spam/off-topic content
11 | Topic Channels | ADIT Exam Discussion | All Users | Topic-specific channel for ADIT exam questions and study tips | ✅ WORKING - Can send/receive messages | ✅ PASS | HIGH | • Add channel description • Pin exam dates and resources • Integrate with exam countdown
12 | Topic Channels | VAT Questions | All Users | Dedicated channel for VAT-related queries | ✅ WORKING - Can send/receive messages | ✅ PASS | HIGH | • Add channel description • Pin VAT resources and guides
13 | Topic Channels | Other Topic Channels | All Users | Transfer Pricing, International Tax, Corporate Tax, Indirect Tax, Tax Technology | ✅ WORKING - All channels functional for messaging | ✅ PASS | MEDIUM | • Add descriptions to all channels • Pin relevant resources • Consider archiving low-activity channels
14 | Topic Channels | Channel Description/Rules | All Users | Each channel shows description, rules, and pinned resources when opened | ❌ NOT IMPLEMENTED - No channel descriptions visible | ❌ FAIL | MEDIUM | • Add channel description header • Show rules and guidelines • Display pinned messages at top
15 | Topic Channels | Channel Search | All Users | Search messages within a specific channel | ❌ NOT IMPLEMENTED - No search functionality | ❌ FAIL | MEDIUM | • Add search bar in channel header • Search message content and authors • Show search results with context
16 | Study Groups | 'Create Group' Button | All Users | Opens modal to create private/public study group with name, description, privacy settings | ⚠️ BACKEND ONLY - Button exists but no modal appears | ⚠️ PARTIAL | MEDIUM | • Create group creation modal • Add fields: name, description, public/private toggle • Generate invite link for private groups • Add members to group automatically
17 | Study Groups | 'My Groups' Section | All Users | Shows list of groups user has joined, with unread message counts | ⚠️ PARTIAL - Section exists but shows test groups, not user's actual groups | ⚠️ PARTIAL | MEDIUM | • Filter groups by user membership • Show unread message badges • Add 'Leave Group' option • Show group member count
18 | Study Groups | Group Invite Links | All Users | Generate shareable link to join private groups | ❌ NOT IMPLEMENTED - No invite link generation | ❌ FAIL | HIGH | • Generate unique invite codes • Create /join/[code] route • Add expiration options • Track who joined via link
19 | Study Groups | Group Discovery | All Users | Browse and join public study groups | ❌ NOT IMPLEMENTED - No group discovery UI | ❌ FAIL | MEDIUM | • Add 'Browse Groups' page • Show group descriptions and member counts • Add 'Join' button for public groups • Filter by topic/exam
20 | Messaging | Send Text Messages | All Users | Type and send messages in channels, appear in real-time | ✅ WORKING - Messages send and appear instantly via Socket.io | ✅ PASS | CRITICAL | • Add message editing (5 min window) • Add message deletion • Add message reactions (emoji)
21 | Messaging | Message Formatting | All Users | Bold, italic, code blocks, links in messages | ❌ NOT IMPLEMENTED - Plain text only, no formatting toolbar | ❌ FAIL | MEDIUM | • Add formatting toolbar • Support Markdown syntax • Add code block syntax highlighting • Auto-link URLs
22 | Messaging | @mentions | All Users | Type @username to mention someone, they get notified | ❌ NOT IMPLEMENTED - No @mention autocomplete or notifications | ❌ FAIL | HIGH | • Add @mention autocomplete • Highlight mentioned users • Send notification to mentioned user • Add 'Mentions' filter
23 | Messaging | Message Threading/Replies | All Users | Reply to specific messages to create threads | ❌ NOT IMPLEMENTED - No reply functionality | ❌ FAIL | MEDIUM | • Add 'Reply' button to messages • Show thread indicators • Collapse/expand threads • Navigate to parent message
24 | Messaging | Typing Indicators | All Users | See 'User is typing...' when someone is composing a message | ⚠️ BACKEND ONLY - Socket.io emits typing events but no UI display | ⚠️ PARTIAL | LOW | • Display typing indicator below message list • Show multiple users typing • Auto-hide after 3 seconds
25 | Messaging | Online User Status | All Users | Green dot next to online users in sidebar | ⚠️ BACKEND ONLY - Socket.io tracks online users but UI shows fake 'User 1-5' | ⚠️ PARTIAL | LOW | • Show real online users (not fake data) • Update status in real-time • Add 'last seen' for offline users
26 | Messaging | Message History/Pagination | All Users | Scroll up to load older messages (infinite scroll or 'Load More') | ⚠️ PARTIAL - Shows recent messages but no pagination | ⚠️ PARTIAL | MEDIUM | • Add 'Load More' button or infinite scroll • Load 50 messages at a time • Jump to date functionality
27 | Messaging | Pinned Messages | All Users | Important messages pinned at top of channel | ⚠️ BACKEND ONLY - Database supports pinning but no UI to pin/view | ⚠️ PARTIAL | MEDIUM | • Add 'Pin Message' button (admin only) • Show pinned messages at channel top • Add 'View All Pinned' modal
28 | Messaging | File/Image Upload | All Users | Attach images, PDFs, documents to messages | ❌ NOT IMPLEMENTED - No file upload button | ❌ FAIL | HIGH | • Add file upload button • Support images, PDFs, docs • Show image previews inline • Use S3 storage (already configured)
29 | Messaging | Message Reactions | All Users | React to messages with emoji (👍, ❤️, 😂, etc.) | ❌ NOT IMPLEMENTED - No reaction functionality | ❌ FAIL | LOW | • Add reaction picker • Show reaction counts • Allow removing reactions • Limit to common emojis
30 | @moji Chatbot | Knowledge Base Responses | All Users | Ask @moji tax questions, get answers from knowledge base + LLM | ✅ WORKING - @moji responds intelligently with context from knowledge base | ✅ PASS | HIGH | • Improve response formatting • Add source citations • Reduce response time (currently 3-5 sec) • Add confidence scores
31 | @moji Chatbot | Visual Styling | All Users | @moji messages have distinct appearance (light blue background, robot icon) | ⚠️ PARTIAL - Has robot emoji but background not styled | ⚠️ PARTIAL | LOW | • Add light blue background to @moji messages • Make robot icon more prominent • Add 'AI Response' label
32 | @moji Chatbot | Escalation to Human | All Users | When @moji can't answer, offers 'Talk to Human' button | ⚠️ BACKEND ONLY - Escalation logic exists but no UI button | ⚠️ PARTIAL | MEDIUM | • Add 'This didn't help' button to @moji messages • Create support ticket on click • Notify admin immediately
33 | @moji Chatbot | Conversation Context | All Users | @moji remembers previous messages in conversation | ⚠️ UNKNOWN - Not tested, unclear if context is maintained | ⚠️ UNKNOWN | MEDIUM | • Test multi-turn conversations • Pass conversation history to LLM • Limit context to last 10 messages
34 | Admin Posting | 'Create Post' Button | Admin | Opens modal to create Events, Announcements, Articles, Newsletters | ⚠️ BACKEND ONLY - Button exists but no modal appears | ⚠️ PARTIAL | HIGH | • Create post creation modal • Add post type selector • Add fields for each post type • Publish to chat feed as message
35 | Admin Posting | Event Posts | Admin | Create events with title, date, time, location, RSVP | ⚠️ BACKEND ONLY - Database schema exists, no UI | ⚠️ PARTIAL | HIGH | • Build event creation form • Add date/time picker • Add RSVP tracking • Send calendar invites
36 | Admin Posting | Announcement Posts | Admin | Create announcements with priority levels, appear at top of feed | ⚠️ BACKEND ONLY - Database schema exists, no UI | ⚠️ PARTIAL | HIGH | • Build announcement form • Add priority selector (high/medium/low) • Pin high-priority announcements • Send email notifications
37 | Admin Posting | Article Posts | Admin | Create articles with title, content, tags, featured image | ⚠️ BACKEND ONLY - Database schema exists, no UI | ⚠️ PARTIAL | MEDIUM | • Build article editor • Add rich text formatting • Add tag system • Show in Articles library
38 | Admin Posting | Newsletter Posts | Admin | Create newsletters with subject, content, distribution list, schedule | ⚠️ BACKEND ONLY - Database schema exists, no UI | ⚠️ PARTIAL | MEDIUM | • Build newsletter editor • Add recipient selector • Add scheduling options • Integrate with email system
39 | Admin Posting | Posts in Chat Feed | All Users | Posts appear as special message cards in chat with metadata (event date, tags, priority) | ❌ NOT IMPLEMENTED - Posts don't appear in chat feed | ❌ FAIL | HIGH | • Auto-create chat message when post is created • Style post messages as cards • Show post metadata • Add 'Read More' link to full post
40 | Admin Posting | Pinned Posts | All Users | Pinned posts stay at top of chat feed | ❌ NOT IMPLEMENTED - No pinned post display | ❌ FAIL | MEDIUM | • Show pinned posts at channel top • Add 'Pinned' badge • Allow unpinning (admin only)
41 | Category Libraries | Articles Library | All Users | Browse all articles in grid layout with search and filters | ❌ NOT IMPLEMENTED - No articles page exists | ❌ FAIL | MEDIUM | • Create /articles route • Build grid layout with cards • Add search and tag filters • Link from sidebar 'Categories' section
42 | Category Libraries | Events Calendar | All Users | View upcoming and past events in calendar view | ❌ NOT IMPLEMENTED - No events calendar | ❌ FAIL | MEDIUM | • Create /events route • Build calendar view • Add RSVP functionality • Show countdown to next event
43 | Category Libraries | Announcements Archive | All Users | Browse past announcements with search | ❌ NOT IMPLEMENTED - No announcements page | ❌ FAIL | LOW | • Create /announcements route • List announcements chronologically • Add search functionality
44 | Admin Area | Admin Login | Admin | Simple login at /auth/admin to access admin dashboard | ⚠️ PARTIAL - Route exists but no password protection | ⚠️ PARTIAL | CRITICAL | • Add password protection • Use environment variable for password • Add session management • Add 'Remember me' option
45 | Admin Area | Admin Dashboard | Admin | Overview stats (users, messages, emails sent), quick links to management sections | ✅ WORKING - Dashboard shows stats cards and navigation | ✅ PASS | MEDIUM | • Show real data (currently placeholder) • Add date range filters • Add export functionality • Add activity graphs
46 | Admin Area | Support Inbox (Admin) | Admin | 'Chat with Team MojiTax' becomes 'Support Inbox' showing all user support tickets | ✅ WORKING - Support Inbox shows tickets with status, priority, user info | ✅ PASS | HIGH | • Add email notifications when new tickets arrive • Add ticket assignment to team members • Add canned responses • Add satisfaction ratings
47 | Admin Area | Chat Analytics Dashboard | Admin | Filter and export chat conversations by type, date, keywords | ✅ WORKING - Analytics page with filters and CSV export | ✅ PASS | MEDIUM | • Add more filter options • Add charts and visualizations • Add sentiment analysis • Add topic clustering
48 | Admin Area | Moji Knowledge Base Management | Admin | Upload CSV, add/edit/delete knowledge base entries | ✅ WORKING - Can upload CSV, search, edit, delete entries | ✅ PASS | HIGH | • Add bulk edit functionality • Add import validation • Add version history • Add testing tool for responses
49 | Admin Area | User Moderation | Admin | View all users, suspend from posting (not expel) | ⚠️ PARTIAL - UI exists but not connected to backend | ⚠️ PARTIAL | MEDIUM | • Connect UI to backend • Add suspension duration options • Add suspension reason field • Send email to suspended users
50 | Admin Area | Email Logs | Admin | View history of all emails sent by platform | ⚠️ PARTIAL - UI exists but shows empty table | ⚠️ PARTIAL | LOW | • Connect to email logs database • Show recipient, subject, status, timestamp • Add resend functionality • Add email preview
51 | Admin Area | Channel Management | Admin | Create, edit, archive channels from admin dashboard | ❌ NOT IMPLEMENTED - No channel management UI | ❌ FAIL | MEDIUM | • Add channel management page • Add create/edit/archive buttons • Add channel reordering • Add member management
52 | Email Notifications | New Support Ticket Email | Admin | Email to admin@mojitax.com when user creates support ticket | ❌ NOT IMPLEMENTED - No email integration | ❌ FAIL | CRITICAL | • Integrate email service (SendGrid/AWS SES) • Send email on ticket creation • Include ticket details and link • Add reply-to-ticket functionality
53 | Email Notifications | Admin Reply Email | Users | Email to user when admin replies to their support ticket (if offline) | ❌ NOT IMPLEMENTED - No email integration | ❌ FAIL | HIGH | • Send email when admin replies • Include message content • Add link to continue conversation • Add unsubscribe option
54 | Email Notifications | Ticket Closed Email | Users | Email transcript when support ticket is marked as resolved | ❌ NOT IMPLEMENTED - No email integration | ❌ FAIL | MEDIUM | • Send email on ticket close • Include full conversation transcript • Add satisfaction survey link • Add 'Reopen' option
55 | Email Notifications | @mention Notifications | All Users | Email notification when someone @mentions you in chat | ❌ NOT IMPLEMENTED - No @mention or email system | ❌ FAIL | MEDIUM | • Implement @mention functionality first • Send email with message context • Add link to jump to message • Add notification preferences
56 | Email Notifications | Announcement Emails | All Users | Email to all users (or specific groups) when admin posts high-priority announcement | ❌ NOT IMPLEMENTED - No email integration | ❌ FAIL | HIGH | • Send email for high-priority announcements • Add distribution list selector • Add email preview • Track open rates
57 | UI/UX | Global Markets Clock | All Users | Header shows current time in Sydney, Tokyo, London, New York | ✅ WORKING - Clock displays and updates in real-time | ✅ PASS | LOW | • Ensure timezone accuracy • Add more cities if needed • Make responsive on mobile
58 | UI/UX | Search Functionality | All Users | Global search for messages, posts, users across platform | ❌ NOT IMPLEMENTED - No search bar | ❌ FAIL | HIGH | • Add search bar in header • Search across channels and posts • Show results grouped by type • Add advanced filters
59 | UI/UX | Mobile Responsive Design | All Users | Platform works well on mobile devices with hamburger menu | ⚠️ UNKNOWN - Not tested on mobile | ⚠️ UNKNOWN | HIGH | • Test on iOS and Android • Optimize touch targets • Add swipe gestures • Test keyboard behavior
60 | UI/UX | Quick Links Sidebar | All Users | Right sidebar shows Community Guidelines, Tax Resources Library, Webinar Calendar, Membership Info | ⚠️ PARTIAL - Links exist but go nowhere (placeholders) | ⚠️ PARTIAL | MEDIUM | • Create actual pages for each link • Add content to resource pages • Make links functional • Add more useful links
61 | UI/UX | Categories Sidebar | All Users | Right sidebar shows Articles, Events with click-to-navigate | ⚠️ PARTIAL - Shows categories but links don't work | ⚠️ PARTIAL | MEDIUM | • Make category links functional • Navigate to category library pages • Show item counts • Add 'View All' links
62 | UI/UX | Exam Countdown | All Users | Shows days until next ADIT exam | ❌ NOT IMPLEMENTED - No exam countdown visible | ❌ FAIL | MEDIUM | • Add exam countdown widget • Pull exam dates from database • Show in sidebar or header • Add 'Add to Calendar' button
63 | UI/UX | Member Count Display | All Users | Shows total number of community members | ❌ NOT IMPLEMENTED - No member count visible | ❌ FAIL | LOW | • Add member count to sidebar • Update in real-time • Show 'X members online'
64 | UI/UX | Floating Action Button (Mobile) | Mobile Users | Quick access to common actions (new message, create post) | ❌ NOT IMPLEMENTED - No FAB on mobile | ❌ FAIL | MEDIUM | • Add FAB for mobile view • Show menu on tap • Include common actions
65 | Security & Compliance | Terms of Service | All Users | Legal terms users must accept before using platform | ❌ NOT IMPLEMENTED - No terms page or acceptance flow | ❌ FAIL | CRITICAL | • Create terms of service page • Add acceptance checkbox on signup • Store acceptance in database • Add link in footer
66 | Security & Compliance | Privacy Policy | All Users | Explains data collection and usage | ❌ NOT IMPLEMENTED - No privacy policy page | ❌ FAIL | CRITICAL | • Create privacy policy page • Explain data collection • Add cookie consent banner • Add link in footer
67 | Security & Compliance | Data Export (GDPR) | All Users | Users can download all their data | ❌ NOT IMPLEMENTED - No data export functionality | ❌ FAIL | HIGH | • Add 'Download My Data' button • Export messages, profile, activity • Provide in JSON or CSV • Complete within 30 days
68 | Security & Compliance | Account Deletion | All Users | Users can delete their account and all data | ❌ NOT IMPLEMENTED - No account deletion option | ❌ FAIL | HIGH | • Add 'Delete Account' button • Show confirmation dialog • Delete all user data • Send confirmation email
69 | Security & Compliance | Rate Limiting | All Users | Prevent spam by limiting message sending rate | ❌ NOT IMPLEMENTED - No rate limiting | ❌ FAIL | MEDIUM | • Add rate limiting middleware • Limit to 10 messages per minute • Show error message on limit • Increase limits for trusted users
70 | Security & Compliance | Content Moderation | Admin | Flag and remove inappropriate content | ❌ NOT IMPLEMENTED - No moderation tools | ❌ FAIL | MEDIUM | • Add 'Report Message' button • Create moderation queue • Add message deletion (admin) • Add user warnings system
71 | Security & Compliance | XSS Protection | All Users | Prevent cross-site scripting attacks in messages | ⚠️ UNKNOWN - Not tested | ⚠️ UNKNOWN | CRITICAL | • Sanitize all user input • Escape HTML in messages • Test with XSS payloads • Use Content Security Policy
72 | Security & Compliance | CSRF Protection | All Users | Prevent cross-site request forgery | ⚠️ UNKNOWN - Not tested | ⚠️ UNKNOWN | HIGH | • Add CSRF tokens to forms • Validate tokens on backend • Test with CSRF attacks
73 | Performance & Reliability | Message Delivery Reliability | All Users | Messages always delivered, even if connection drops | ⚠️ UNKNOWN - Not tested with connection issues | ⚠️ UNKNOWN | HIGH | • Add message queuing • Retry failed sends • Show delivery status • Test with poor connections
74 | Performance & Reliability | Offline Support | All Users | Platform works offline, syncs when reconnected | ❌ NOT IMPLEMENTED - No offline support | ❌ FAIL | MEDIUM | • Add service worker • Cache messages locally • Queue outgoing messages • Show offline indicator
75 | Performance & Reliability | Load Time Optimization | All Users | Platform loads in under 3 seconds | ⚠️ UNKNOWN - Not tested | ⚠️ UNKNOWN | MEDIUM | • Measure load times • Optimize bundle size • Add lazy loading • Use CDN for assets
76 | Performance & Reliability | Database Query Optimization | All Users | Fast message loading even with thousands of messages | ⚠️ UNKNOWN - Not tested at scale | ⚠️ UNKNOWN | MEDIUM | • Add database indexes • Optimize queries • Add query caching • Load test with 10k+ messages
77 | Performance & Reliability | Error Handling & Logging | All Users | Graceful error messages, errors logged for debugging | ⚠️ PARTIAL - No user-facing error messages | ⚠️ PARTIAL | MEDIUM | • Add toast notifications for errors • Log errors to monitoring service • Add error boundaries • Show helpful error messages
78 | Performance & Reliability | Monitoring & Alerts | Admin | Real-time monitoring of platform health, alerts for issues | ❌ NOT IMPLEMENTED - No monitoring | ❌ FAIL | HIGH | • Integrate monitoring service (Sentry, LogRocket) • Set up uptime monitoring • Add error rate alerts • Monitor Socket.io connections